## ProjectTeam
Work Load
Name | GitHub Alias | Funktion | Sprint #1
Däppen, Michael | damichu | Dev | 7
Dressler, Armon | tetanushamster | Dev | 8
Kündig, Moritz | kundm2 | Dev | 7
Pulfer, Samuel | samuelpulfer | SCRUM Master, Dev | 9
Tschanz, Roger | tschr3 | Dev | 9
Vogel, Jürgen | vgj1 | Product Owner | 0
Pfarrer, Marcel | prm2 | Product Owner | 0
all |  |  | 5

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original (in h) | Effort Plan Updated (in h) | Effort Actual (in h) | Status
1 | Minimalsystem | - Patientenverwaltung - Fallmanagement - Diagnose - Anamnese - Appointement | High | 45 |  |  | Not started
2 | Case Report | Case Report aufgrund von Regeln / Favorisierung -> Favorisierung innerhalb Cases Entscheidungslogik für Report Elemente - Fallmanagement - Drugs - Labor | Med | 70 |  |  | Not started
3 | Messages | Nachrichten bei Patientenzugriff (-> Informationsfluss) | Low | 35 |  |  | Not started
150

## Sprint Backlog
Sprint | ID | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
Total 🡒 | 0 | [6 empty] | 45 | 0 | 0
1 | 1 | Base System Main View | Functioning Vaadin Enviroment | Base System | all |  | High | 5 |  |  | new
1 | 2 | Screen Design Main View | Create Main View "Homepage", based on prototype | Mock-Up / Presentation | Pulfer, Samuel |  | High | 2 |  |  | new
1 | 3 | Screen Design patient details | Create Patientlist (P1, P2, etc.) based on prototype | Mock-Up / Presentation | Pulfer, Samuel |  | High | 1 |  |  | new
1 | 4 | Screen Design case details | Create Caselist (F1, F2, F3) based on prototype | Mock-Up / Presentation | Pulfer, Samuel |  | medium | 1 |  |  | new
1 | 5 | Screen Design dialog boxes | Includes general building (diagnosis, anamnesis, calendar, etc) | Mock-Up / Presentation | Pulfer, Samuel |  | low | 1 |  |  | new
1 | 6 | Class Patient | Create Patientlist according to the Mock-Up. Includes Class natPerson (Task Screen Design patient details) | Base System | Pulfer, Samuel |  | medium | 2 |  |  | new
1 | 7 | Class Case | Create Caselist according to the Mock-Up. Includes Class natPerson (Screen Design case details) | Base System | Tschanz, Roger |  | medium | 2 |  |  | new
1 | 8 | Class Case Details | Create the InfoBoxes Diagnosis, Anamnesis, Appointement of each Case according to the Mock-Up (Task Screen Design dialog boxes) | Base System | Kündig, Moritz |  | medium | 1 |  |  | new
1 | 9 | Presentation Patient | Shows patient details | Presentation | Dressler, Armon |  | medium | 4 |  |  | new
1 | 10 | Presentation Case | Show case details | Presentation | Däppen, Michael |  | medium | 4 |  |  | new
1 | 11 | InfoBox Diagnosis | Shows diagnosis within case details | Presentation | Pulfer, Samuel |  | low | 2 |  |  | new
1 | 12 | InfoBox Anamnesis | Shows anamnesis within case details | Presentation | Kündig, Moritz |  | low | 2 |  |  | new
1 | 13 | InfoBox Appointment | Shows appointement within case details | Presentation | Tschanz, Roger |  | medium | 3 |  |  | new
1 | 14 | Appointment Calendar | Includes a calendar for the Appointment InfoBox | Base System | Däppen, Michael |  | medium | 3 |  |  | new
1 | 15 | DB - Semantic Modeling | Modeling the ERD (entities, relationships, attributes) | Model | Dressler, Armon |  | High | 4 |  |  | new
1 | 16 | DB - Logical Modeling | Modelling the DB-ORM | Model | Kündig, Moritz |  | High | 4 |  |  | new
1 | 17 | DB - Implementation | Implementing the model including. constraints, indexes, etc. | Model | Tschanz, Roger |  | High | 4 |  |  | new